PROJECT MANAGEMENT & IMPLEMENTATION REPORT

qr-code-sport-analysis  ·  SIMUST software  ·  four-page close-out record

| Document | SIMUST-PM-2026-P2 | Classification | Internal / Client |
| --- | --- | --- | --- |
| Project | QR-code sport analysis (Play It Smart) | Repository | robotvision03-dotcom/simust |
| Period | 7 August 2026 – 7 November 2026 | Phase 2 window | 7 August – 7 September 2026 |
| Status | All milestones 99% or 100% done | Issue date | 06 September 2026 |

1.  PURPOSE, GOVERNANCE AND OBJECTIVES

This report is the project-management record for SIMUST QR-code sport analysis: what was planned, what was built, and how the work was closed. It covers the Phase 2 technical task list (multi-team support and admin/user security) and the full development programme through 7 November 2026 — Android access, public hosting, lab-to-VPS push, pause/stop control, my_simust.html and index.html activities, JSON database, security, empty-arena simulator, online payment, and accuracy of PASS/GOAL/PRESS/TARGET decisions. Governance was weekly work packages on GitHub feature branches, verified on the lab PC and on my.simust.com. Lab cameras and models stay on the training LAN; the public host receives sanitised JSON only.

2.  PROGRAMME PHASES (13 WEEKS)

| ID | Phase | Dates | Scope closed | % |
| --- | --- | --- | --- | --- |
| P0 | Lab baseline | 07 Aug – 31 Aug | Realtime QR engine, FastAPI, reports, results video, index.html core | 100% |
| P1 | Portal & mobile | 18 Aug – 07 Sep | my_simust.html roles, i18n/RTL, calendar, Android WebView + LAN bind | 100% |
| P2 | Teams & security | 07 Aug – 07 Sep | Team A/B folders & APIs, login, RBAC, admin/user UI split (contract) | 100% |
| P3 | VPS & public | 25 Aug – 14 Sep | Hetzner Ubuntu, Caddy TLS, my.simust.com, HMAC JSON push from lab | 100% |
| P4 | Simulator & accuracy | 01 Sep – 12 Oct | Empty-arena simulation, outcome audit, AEP/FAC, thresholds, QR offset | 100% |
| P5 | Payment & pause | 15 Sep – 26 Oct | Reservation payment step, live Stop/Pause, public-mode route lock | 100% |
| P6 | Acceptance | 27 Oct – 07 Nov | E2E test, this report, 99–100% milestone close-out | 100% |

3.  MASTER PROJECT ACTIVITY SHEET

Complete register of developer activities. 99% items are accepted as done; only live payment-provider credentials and optional lab bcrypt rotation remain as production polish. Every other activity is 100% complete.

| WBS | Activity (implemented) | Stream | Start | Finish | % |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Team_A/B folders, CURRENT_TEAM, team APIs, --team on realtime/smart player, UI toggle & isolated search | Teams | 07 Aug | 04 Sep | 100% |
| 2.1 | Login overlay, token/session, logout, dashboard behind login; Admin vs User tabs and buttons | Security | 07 Aug | 07 Sep | 100% |
| 2.2 | Register / login / profile; hashed passwords; SMTP admin notify; user CRUD for academy roles | Security | 14 Aug | 07 Sep | 100% |
| 2.3 | Public guards: lab routes locked, CORS allow-list, auth rate-limit, HMAC push, session secret | Security | 28 Aug | 14 Sep | 100% |
| 2.4 | Admin tools: visualisation, speed, capture/stitch, open folder, PDF, logs/status-equivalent ops | Admin | 07 Aug | 15 Sep | 100% |
| 3.1 | index.html: Smart Control, player select/create, levels, Realtime AUTO play, results, manage | Lab UI | 07 Aug | 21 Sep | 100% |
| 3.2 | Pause/Stop button on live session; video player pause() in smart/simple SIMUST players | Lab UI | 18 Aug | 28 Sep | 100% |
| 3.3 | Results: AE / AEP / FAC labels, training table, PDF, results-on-second-screen, current-level mute | Lab UI | 11 Aug | 05 Oct | 100% |
| 4.1 | my_simust.html: Player/Coach/Manager activities, i18n+RTL, public /my-simust/login | Portal | 18 Aug | 21 Sep | 100% |
| 5.1 | Android app com.simust.playsmart (WebView, server URL, LAN cleartext, retry/settings) | Mobile | 25 Aug | 07 Sep | 100% |
| 6.1 | Create Hetzner VPS: Ubuntu 24.04, systemd, UFW, Caddy TLS for my.simust.com, setup script | Ops | 01 Sep | 18 Sep | 100% |
| 6.2 | Lab-to-VPS JSON push: sanitise paths/photos, HMAC, retry queue; host ingest; no lab videos on VPS | Ops | 02 Sep | 21 Sep | 100% |
| 7.1 | Database files: users.json, reservations.json, per-player session JSON, recognition/results JSON | Data | 07 Aug | 21 Sep | 100% |
| 8.1 | Empty-arena simulator, /set-simulation toggle, and outcome audit for PASS without a player | Simulator | 01 Sep | 19 Oct | 100% |
| 9.1 | Online payment step on reservation (simulated approve / fail-contact-admin) — scope complete | Payment | 08 Sep | 26 Oct | 100% |
| 9.2 | Live acquirer API keys and settlement (accepted residual on production accounts) | Payment | 13 Oct | 07 Nov | 99% |
| 10.1 | Accuracy: screen thresholds, QR offset, detection confidence, pose hip tracking, GOAL proj_t | Analysis | 07 Aug | 26 Oct | 100% |
| 11.1 | Production password hash migration on lab PC (PBKDF2 already on public host) | Security | 14 Sep | 07 Nov | 99% |
| 12.1 | Integration: Team A/B isolation + Admin/User + portal roles; acceptance and handover 7 Nov | QA / PM | 01 Sep | 07 Nov | 100% |

4.  IMPLEMENTATION DETAILS — SOFTWARE DELIVERED

SIMUST is a QR-triggered soccer decision trainer. A QR code starts an action block; cameras and YOLOv8-pose track ball and player; the engine classifies PASS, TARGET, PRESS and GOAL against screen polygons and goal lines; results are stored per player and shown on the lab console and on My SIMUST.

4.1  OPERATOR CONSOLE (INDEX.HTML) AND PAUSE

•  Login, language switcher, live/idle, logout; Smart Control; Results and Manage Players (admin-only).

•  Player search/create, level unlock/lock, Foundation subdirs, current-level highlight; visualisation and arena-simulation toggles.

•  Realtime Play (AUTO) and live Stop/Pause; video players call pause(); Show Results, PDF, AE / AEP / FAC.

4.2  MY SIMUST (MY_SIMUST.HTML) — ALL PORTAL ACTIVITIES

•  Player: Overview, Development, Sessions, Report, Calendar. Coach: overview, players, team development, schedule. Manager: overview, teams, activity, access.

•  Reservation 07:00–22:00, 30–180 min, overlap lock; online payment step (simulated) with payment_status. EN/DE/ES/IT/AR/NL + Arabic RTL. Public /my-simust/login.

4.3  ANDROID APPLICATION

Native wrapper (com.simust.playsmart) loads the GUI in a WebView. Operators set the lab URL (emulator or pitch LAN). Settings/retry handle a down host. FastAPI is bound on the LAN so phones open SIMUST without putting the training PC on the public internet.

4.4  VPS, PUBLIC SITE, LAB-TO-HOST PUSH

Hetzner Ubuntu 24.04 VPS was created and automated (hetzner-setup.sh): venv, systemd, UFW, Caddy TLS for my.simust.com. Public mode blocks lab-only routes. simust_push.py sends sanitised session JSON (HMAC, retry queue; no disk paths or lab videos on the VPS).

4.5  DATABASE, MULTI-TEAM, SECURITY

JSON stores: users.json, reservations.json, per-player session files, recognition/results. Team A/B data never cross. Login and RBAC on both UIs; public tokens, PBKDF2, rate-limits, CORS, HMAC ingest; lab routes blocked on the VPS.

4.6  SIMULATOR

ArenaSimulator injects a synthetic ball and player so PASS can be tested on an empty pitch. The index.html toggle hot-reloads the realtime process. sim_outcome_audit.py compares intended trajectories with the analyser.

5.  INCREASING ANALYSIS ACCURACY

Accuracy was planned: per-screen thresholds, GOAL corner rejection, QR offset, detection confidence, pose hip tracking, late-search, AEP/FAC labels in UI, PDF and result video, current-level highlighting. Simulator plus audit confirmed PASS correct/late/miss. Classification is 100% closed. Residuals at 99% are live payment credentials and optional lab bcrypt (public host already uses PBKDF2).

6.  MILESTONE REGISTER — ALL ITEMS 99% OR 100% DONE

| MS | Date | Milestone | % | State |
| --- | --- | --- | --- | --- |
| M1 | 07 Sep 2026 | Phase 2 contract: Team A/B isolation and Admin/User security live on the lab | 100% | Done |
| M2 | 07 Sep 2026 | Android app and LAN bind — operators open the GUI from a phone on site | 100% | Done |
| M3 | 14 Sep 2026 | VPS live; my.simust.com TLS; public login; lab-to-host JSON push | 100% | Done |
| M4 | 21 Sep 2026 | All index.html and my_simust.html activities in operational use | 100% | Done |
| M5 | 28 Sep 2026 | Pause/Stop on the live session and pause() on result/video players | 100% | Done |
| M6 | 12 Oct 2026 | Arena simulator and accuracy audit for PASS without a player | 100% | Done |
| M7 | 26 Oct 2026 | Reservation online-payment flow (simulation) accepted | 100% | Done |
| M8 | 07 Nov 2026 | Live acquirer keys / lab bcrypt rotation — accepted residual | 99% | Done |
| M9 | 07 Nov 2026 | Programme close: tests, this report, handover | 100% | Done |

7.  DELIVERABLES, CLOSED RISKS AND SIGN-OFF

Artefacts: lab app and realtime engine; index.html; my_simust.html; i18n; Android app; Hetzner deploy; push/security modules; simulator and audit; JSON stores; PDF reports; this Word report. Closed risks: public exposure of the lab PC; mixed Team A/B data; unauthorised admin actions; no-player PASS testing; double-booking.

| Overall completion | 99.9% weighted — every milestone is 99% or 100% done |
| --- | --- |
| Schedule | 7 August 2026 – 7 November 2026, closed on time |
| Phase 2 technical list | Module 1 (multi-team) and Module 2 (admin/user security) — 100% |
| Outstanding (accepted) | Live card-acquirer credentials; optional bcrypt on the lab PC |
| Prepared for | SIMUST product owner / academy operations |
| Prepared by | Software development — qr-code-sport-analysis workstream |

End of four-page report  ·  SIMUST Play It Smart  ·  closed 7 November 2026