PROJECT MANAGEMENT & IMPLEMENTATION REPORT

qr-code-sport-analysis  ·  SIMUST software  ·  pay period 7 Sep – 6 Oct

| Document | FHP-PM-2026-P3 | Classification | Internal / Client |
| --- | --- | --- | --- |
| Project | SIMUST | Repository | robotvision03-dotcom/simust |
| Period | 7 September 2026 – 6 October 2026 | Contract window | 4 weeks (Phase 3 technical delivery) |
| Status | All milestones 99% or 100% done | Issue date | 05 October 2026 |

1.  PURPOSE, GOVERNANCE AND OBJECTIVES

This report is the project-management record for SIMUST QR-code sport analysis in the payment period 7 September – 6 October 2026. It continues Phase 2 close-out and records Phase 3 delivery: dual Field A/B realtime, image-cue keypoint sync (17-frame delay, 20/30 FPS), booking-gated play, Foundation→Entry→World Class unlock, coach/operator reservations, My SIMUST Android (Google Play bundle), phone-first operator UX, finish-balls coaching films, pause-freeze accuracy, and live RESULTS. Governance used GitHub feature branches (Field_A_B, image_based_player, version3, entry, version4, finish_balls, centralization, qr_sync) merged to main after lab and my.simust.com checks. About 70 developer commits across all branches in this window were reviewed for this close-out.

2.  PROGRAMME PHASES (4 WEEKS: 7 SEPTEMBER – 6 OCTOBER 2026)

| ID | Phase | Dates | Scope closed | % |
| --- | --- | --- | --- | --- |
| P0 | Dual-field realtime | 07 Sep – 16 Sep | Field A/B synced play, single-field mode, combined results | 100% |
| P1 | Booking & portal | 09 Sep – 16 Sep | Booking windows, staff reservations, portal i18n/freeze fixes | 100% |
| P2 | Image-cue player | 18 Sep – 25 Sep | Teammate flash, 17f keypoint delay, 20 FPS clock, SF labeled player | 100% |
| P3 | Levels & unlock | 10 Sep – 29 Sep | Paid unlock, Entry A-T series, score-gated next set to World Class | 100% |
| P4 | Coach & mobile UX | 26 Sep – 05 Oct | Coach reservations/levels, phone operator, My SIMUST Play bundle | 100% |
| P5 | Accuracy & pause | 08 Sep – 05 Oct | GOAL/PRESS/late tempo, keypoint sync, pause freeze + resume math | 100% |
| P6 | Acceptance | 03 Oct – 06 Oct | Finish-balls coaches, unlock sims, this PM report, handover | 100% |

3.  MASTER PROJECT ACTIVITY SHEET

Complete register of developer activities in this pay window. Reviewed from all active branches (main, Field_A_B*, image_based_player*, version3*, entry, version4, finish_balls, centralization, qr_sync, cursor/*). 99% items are accepted residuals only.

| WBS | Activity (implemented) | Stream | Start | Finish | % |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Dual Field A/B realtime: synced sessions, combined results, active-only detection/labels | Dual field | 07 Sep | 16 Sep | 100% |
| 1.2 | Single-field A or B start from remote operator; inactive half masked; B coach slices | Dual field | 13 Sep | 26 Sep | 100% |
| 1.3 | Screens renamed 1–6 per field; content centered with saved calibration; Insta button | Dual field | 26 Sep | 27 Sep | 100% |
| 2.1 | Gate Realtime Play to live booking windows; dual calendars; hide other players' names | Booking | 13 Sep | 16 Sep | 100% |
| 2.2 | Staff reservation management tab; coach password cancel/add; multi-slot calendar UX | Booking | 15 Sep | 05 Oct | 100% |
| 2.3 | Admin/coach play-without-reservation (test password) after player select | Booking | 16 Sep | 05 Oct | 100% |
| 3.1 | Image-based teammate-flash player; cue-driven keypoints; SF-30N labeled action/gap | Player | 22 Sep | 25 Sep | 100% |
| 3.2 | 17-frame keypoint delay per pass; 20 FPS clock; stop video after last pass; QR sync tune | Player | 18 Sep | 25 Sep | 100% |
| 3.3 | Foundation cognitive/math playlists; mixed Foundation remote start; opening cards A/B | Player | 23 Sep | 26 Sep | 100% |
| 4.1 | Paid 30-minute unlock pipeline; score opens next set; A-T4 opens next band (Entry→Activated…) | Progress | 10 Sep | 05 Oct | 100% |
| 4.2 | Entry dual-field unlock; Elite/World Class order; finish-balls clock + coach films | Progress | 26 Sep | 03 Oct | 100% |
| 5.1 | My SIMUST Android (com.simust.mysimust): login/dashboard, waiver, Play signed AAB | Mobile | 10 Sep | 11 Sep | 100% |
| 5.2 | Operator Android SIMUST 2.4→2.13: lab-link status, cache bust, phone-first operator UI | Mobile | 08 Sep | 05 Oct | 100% |
| 6.1 | my.simust.com production hostname; VPS update script branch arg; deploy pipeline docs | Ops | 08 Sep | 26 Sep | 100% |
| 6.2 | Remote coach login harden; hide visualisation for coaches; lab failure surfacing | Ops | 08 Sep | 05 Oct | 100% |
| 7.1 | Accuracy: GOAL corner Miss, PRESS Correct no Miss, tempo-aware late search, SF-30N labels | Analysis | 08 Sep | 10 Sep | 100% |
| 7.2 | Pause freeze: countdown/session/analysis clocks + player action timers; resume shift math | Analysis | 09 Sep | 05 Oct | 100% |
| 7.3 | Homography in git; SF-60N displacement/replay tests; wrong-action own-screen results | Analysis | 09 Sep | 28 Sep | 100% |
| 8.1 | Portal/operator i18n repair; dashboard freeze fixes; live RESULTS while session runs | UI | 08 Sep | 15 Sep | 100% |
| 8.2 | Phone operator: coach password checkbox, select player Field A/B, hamburger logout, Reservation | UI | 05 Oct | 05 Oct | 100% |
| 9.1 | Unlock / dual-field / pause simulators and reports; PR merges #13–#18; acceptance handover | QA / PM | 09 Sep | 06 Oct | 100% |
| 9.2 | Live card-acquirer credentials on production (accepted residual from Phase 2) | Payment | 07 Sep | 06 Oct | 99% |

4.  IMPLEMENTATION DETAILS — SOFTWARE DELIVERED

In this period SIMUST moved from single-field lab play to dual-field image-cue training with booking-gated remote operators. Cameras and pose stay on the lab LAN; my.simust.com and Android apps drive play and reservations. Classification of PASS/GOAL/PRESS/TARGET remains the core accuracy product, now with tempo-aware late windows and pause-safe clocks.

4.1  DUAL FIELD A/B AND REMOTE OPERATOR

•  Synced dual realtime; staff can start Field A, Field B, or both; inactive half blacked out.

•  Remote operator: mixed Foundation, Entry A-T display, play-without-reservation, coach login.

•  Phone-first index.html: Select player field A/B, coach password checkbox, Reservation multi-slot calendar, logout in ☰.

4.2  IMAGE-CUE PLAYER, KEYPOINTS AND FINISH-BALLS

•  Teammate-flash / SF labeled player: cue ON → 17-frame keypoint appear, On hold, clear; 20/30 FPS recording.

•  Per-pass delay without slipping later actions; QR sync for dual vs single field.

•  Finish-balls: session clock × actions; matching coach film on final results; wrong action on own screen.

4.3  PROGRESSION, ANDROID AND VPS

•  Score unlock: Foundation SF chain → Entry; A-T4 opens next band; Elite/World Class ordered.

•  My SIMUST Play-ready AAB; operator SIMUST 2.13; update-all.ps1 / update-vps.sh branch-aware.

•  Coach reservations and level control; visualisation admin-only; lab-link online blinking status.

5.  INCREASING ANALYSIS ACCURACY

Accuracy work this period: GOAL near-miss exits as Miss with corner aim; PRESS reach scored Correct without Miss; late search tempo-aware for short/fast SF-30N; SF-30N T1.2 result labels restored; displacement aggregation and QR flicker extras fixed; pause cancels analysis timers and restores remaining delay so Correct/Late windows do not consume pause wall-clock; keypoint On countdown is frame-based and frozen while paused. Simulator tests (unlock-to-World-Class, dual-field, pause) confirm the gates. Residual 99%: live payment acquirer credentials only.

6.  MILESTONE REGISTER — ALL ITEMS 99% OR 100% DONE

| MS | Date | Milestone | % | State |
| --- | --- | --- | --- | --- |
| M1 | 10 Sep 2026 | Paid unlock pipeline and tempo-aware late search for SF-30N | 100% | Done |
| M2 | 11 Sep 2026 | My SIMUST Android + Google Play signed release support | 100% | Done |
| M3 | 16 Sep 2026 | Dual Field A/B realtime merged (PRs #15–#18); booking-gated play | 100% | Done |
| M4 | 22 Sep 2026 | Image-based teammate-flash player and keypoint On sync | 100% | Done |
| M5 | 25 Sep 2026 | 17-frame per-pass delay; 20 FPS clock; Foundation cognitive playlists | 100% | Done |
| M6 | 26 Sep 2026 | Remote mixed Foundation/Entry; screen 1–6 calibration; VPS branch update | 100% | Done |
| M7 | 29 Sep 2026 | Score opens next set through Elite / World Class in order | 100% | Done |
| M8 | 03 Oct 2026 | Finish-balls sessions and matching coach final films | 100% | Done |
| M9 | 05 Oct 2026 | Coach operator + phone UX + A-T4 next-band unlock + SIMUST 2.13 | 100% | Done |
| M10 | 06 Oct 2026 | Pause accuracy simulators; this Phase 3 PM report; handover | 100% | Done |
| M11 | 06 Oct 2026 | Live acquirer keys — accepted residual | 99% | Done |

7.  DELIVERABLES, CLOSED RISKS AND SIGN-OFF

Artefacts: dual-field realtime engine; image-cue smart player; index.html phone operator; my_simust.html booking/portal; My SIMUST + SIMUST Android; VPS deploy scripts; unlock/pause/dual-field tests; this Word report on branch docs/project-management-7sep-6oct. Closed risks: desynced Field A/B clocks; keypoint slip across passes; play outside booking; coach without reservation tools; pause eating late-analysis time; dashboard freeze after login.

| Overall completion | 99.9% weighted — every milestone is 99% or 100% done |
| --- | --- |
| Schedule | 7 September 2026 – 6 October 2026, closed on time |
| Phase 3 technical list | Dual field, image-cue player, unlock chain, coach/mobile UX — 100% |
| Branches reviewed | main, Field_A_B*, image_based_player*, version3*, entry, version4, finish_balls, centralization, qr_sync, cursor/* |
| Outstanding (accepted) | Live card-acquirer credentials on production accounts |
| Prepared for | SIMUST product owner / Siamak Azadi |
| Prepared by | Omid Moradtalab - Software development — qr-code-sport-analysis workstream |

End of four-page report  ·  SIMUST Play It Smart  ·  closed 6 October 2026